## Implementation Schedule
IMPLEMENTATION SCHEDULE
|  |  | PHASE 1 | [11 empty] | PHASE 2
No | Deliverables 1 (D-..) | Months | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24 | M25 | M26 | M27 | M28 | M29 | M30 | M31 | M32 | M33 | M34 | M35 | M36
|  | -1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
Contract Effective Date
Kick Off Meeting
D-1 | Phase 1
D-1-1 | Site Survey
D-1-2 | Base Design
D-1-3 | Equipment Manufacturing
D-1-4 | Factory Acceptance Test
D-1-5 | Detailed Design
D-1-6 | Site Installation & Adaptation Work
D-1-7 | Main Substations (RTU)
D-1-8 | Site Installation NDC (SCADA)
D-1-9 | Testing and Commissioning
D-1-10 | Training
D-1-11 | Point-T-Point Test
D-1-12 | End-T-End Test
D-1-13 | AGC/LFC/EMS Tuning
D-1-14 | Site Acceptance Test
D-1-15 | Trial on Test
D-1-16 | Go Live
D-2 | Phase 2
D-2-1 | Detailed Design
D-2-2 | Site Installation & Adaptation Work
D-2-3 | (PMUs) installation
D-2-4 | Site Installation NDC, BNDC & RDCs (SCADA)
D-2-5 | Testing and Commissioning NDC and BNDC
D-2-6 | WAMS Integration
D-2-7 | Testing and Commissioning RTUs and PMUs
D-2-8 | Training
D-2-9 | Point-T-Point Test
D-2-10 | End-T-End Test
D-2-11 | Site Acceptance Test
D-2-12 | AGC/LFC/EMS Tuning
D-2-13 | Trial on Test
D-2-14 | Warranty Period